## Report
Test Project | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
Earned Value Management Template
| Prepared By: | [Manager's Name] | [12 empty] | © 2012 Vertex42 LLC
| Date: | [Report Date]
[42]
| For Period: | Week 7
Summary:
[Use this space to write a brief summary or to record specific observations or notes]
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Task 1 | 3500 | 1000 | 500 | 2000 | [9 empty] | ← Enter or edit values in the light-blue cells.
1.2 | Task 2 | 4200 |  | 500 | 800 | 900 | 2000
1.3 | Task 3 | 4500 |  |  | 700 | 2000 | 1000 | 800
1.4 | Task 4 | 3300 |  |  | 200 | 600 | 1000 | 1500
1.5 | Task 5 | 3000 |  |  |  |  | 700 | 500 | 1000 | 800
1.6 | Task 6 | 6700 | [7 empty] | 700 | 2000 | 1000 | 2000 | 1000
0
0
0
0
0
0
Insert new rows above this one | [14 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 25200 | 1000 | 1000 | 3700 | 3500 | 4700 | 2800 | 1000 | 1500 | 2000 | 1000 | 2000 | 1000
|  | Cumulative Planned Value (PV) | 1000 | 2000 | 5700 | 9200 | 13900 | 16700 | 17700 | 19200 | 21200 | 22200 | 24200 | 25200
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 800 | 1950 | 4550 | 6550 | 10800 | 13600 | 14500 | [5 empty] | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 525 | 2800 | 5885 | 7820 | 9725 | 15170 | 20770 | [5 empty] | ← Enter the Earned Value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -275 | 850 | 1335 | 1270 | -1075 | 1570 | 6270 | - | - | - | - | -
|  | Schedule Variance (SV = EV - PV) | -475 | 800 | 185 | -1380 | -4175 | -1530 | 3070 | - | - | - | - | -
|  | Cost Performance Index (CPI = EV/AC) | 0.65625 | 1.4359 | 1.2934 | 1.1939 | 0.90046 | 1.1154 | 1.4324 | - | - | - | - | -
|  | Schedule Performance Index (SPI = EV/PV) | 0.525 | 1.4 | 1.0325 | 0.85 | 0.69964 | 0.90838 | 1.1734 | - | - | - | - | -
|  | Estimated Cost at Completion (EAC) | 38400 | 17550 | 19483.4325 | 21107.4169 | 27985.6041 | 22591.9578 | 17592.6818 | - | - | - | - | -
This project is under budget and ahead of schedule.
Note on G20: • Budgeted cost of work scheduled (BCWS): The planned (budgeted) cost of work that should have been completed to date.
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Task 1 | 3500 | 15% | 50% | 100% | 100% | 100% | 100% | 100%
1.2 | Task 2 | 4200 |  | 25% | 30% | 60% | 75% | 90% | 100%
1.3 | Task 3 | 4500 |  |  | 25% | 40% | 50% | 100% | 100%
1.4 | Task 4 | 3300 |  |  |  |  | 25% | 80% | 90%
1.5 | Task 5 | 3000 | [5 empty] | 25% | 75%
1.6 | Task 6 | 6700 | [6 empty] | 50%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 525 | 2800 | 5885 | 7820 | 9725 | 15170 | 20770 | 0 | 0 | 0 | 0 | 0
Note on C7: Earned Value (EV): The percent of the total budget actually completed at a point in time. This is also known as the budgeted cost of work performed (BCWP). EV is calculated by multiplying the budget for an activity by the percent progress for that activity: EV = % complete x budget.

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Task 1 |  | Wk 1: 800; Wk 2: 250; Wk 3: 1500
1.2 | Task 2 |  | Wk 2: 900; Wk 3: 700; Wk 4: 1200; Wk 5: 1700
1.3 | Task 3 |  | Wk 3: 300; Wk 4: 300; Wk 5: 1250; Wk 6: 1500
1.4 | Task 4 |  | Wk 3: 100; Wk 4: 500; Wk 5: 900; Wk 6: 700; Wk 7: 400
1.5 | Task 5 |  | Wk 5: 400; Wk 6: 600; Wk 7: 500
1.6 | Task 6
- | -
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 800 | 1150 | 2600 | 2000 | 4250 | 2800 | 900 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 800 | 1950 | 4550 | 6550 | 10800 | 13600 | 14500 | 14500 | 14500 | 14500 | 14500 | 14500
Note on D7: • Actual cost of work performed (ACWP): The actual cost of the tasks that have been completed.

## Simple EVA Table
Earned Value and its use in Cost Control.
Work Package | BCWS | ACWP | %Progress | BCWP | ACWP : Actual Cost of Work Performed
| Planned Value | Actual Cost |  | Earned Value | BCWP : Budgeted cost of Work Performed
1 | 100000 | 120000 | 100% | 100000 | BAC : Budget At Completion
2 | 100000 | 110000 | 100% | 100000
3 | 100000 | 80000 | 90% | 90000 | BAC | 1000000
4 | 100000 | 125000 | 80% | 80000 | PV | 500000
5 | 100000 | 75000 | 50% | 50000 | AC | 510000
6 | 100000 | 0 | 0% | 0 | EV | 420000
7 | 100000 | 0 | 0% | 0
8 | 100000 | 0 | 0% | 0 | Cost Variance (CV = EV - AC) | Cost Variance (CV = EV - AC) | Cost Variance (CV = EV - AC) | -90000
9 | 100000 | 0 | 0% | 0 | Cost Performance Index (CPI = EV/AC) | Cost Performance Index (CPI = EV/AC) | Cost Performance Index (CPI = EV/AC) | 0.82353
10 | 100000 | 0 | 0% | 0 | Schedule Variance (SV = EV - PV) | Schedule Variance (SV = EV - PV) | Schedule Variance (SV = EV - PV) | -80000
BAC | 1000000 | 510000 |  | 420000 | Schedule Performance Index (SPI = EV/PV) | Schedule Performance Index (SPI = EV/PV) | Schedule Performance Index (SPI = EV/PV) | 0.84
In this example, the project is over budget and behind schedule